## BURNDOWN CHARTS
SPRINT 1
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (0,1,2,3,5,8) | Priority | Risk | Responsible | Due Date
#1 | User should be able to register an account by creating a username and a password so that the user can access to the Peer Assessment Platform | - Add register page which asks user if user is instructor or student, along with their name, username, and password - Add needed columns to database -Register page css | 5- The user needs to be able to register for an account. Otherwise, the user cannot access the Peer Assessment Platform. Required for initializing a profile and taking advantage of the main fucntion of the app. | HIGH | HIGH- part of main function of the website | Frontend: Talar, Valeria Backend: Mohammed | Sept. 20
#2 | User should get a nice error message when the username is no longer available or when the password format is wrong to finalize their registration | - Make it so when user enters a username no longer available, instead they are brought back to the register page and get a nice error message there. | 4- The user needs to be notified if their username/password meets the requirements to register for an account | MED | HIGH- It is important for users to be notified. Howver, it is not a feature with the most priority. | Joseph | Sept. 20
#3 | User should get a nice error message when the username and password does not match a user when logging in | - Make it so when user enters a username and password not found, they are brought back to the login page with a nice error message there. | 4- The user should be notified about their entry being denied due to the username/password not matching as it is the foundation of one's entry to the webiste | MED | HIGH- It is extremely important for this step to be implemented as it allow users to be granted use of the website | Joseph | Sept. 25
#4 | User should be able to login with their credentials so that they can access the platform | - Add login page which asks user their username and password, communicates with database and gives user session variables - Login page frontend | 4- Same idea as issue#2 and issue#3 | HIGH- Essential for registered users to login onto the Peer Assement platform to be able to access its function. Part of the main part of the website. | HIGH- Messing up this task implies that the website won't work | Frontend: Talar, Valeria Backend: Samuel | Sept. 22
#5 | Instructor should see their own home page | - Make instructor home page -Home page frontend | 3- The home page requires a fullstack developpement in which the layout and design of the website needs to be implemented while differentiaing between the pages of the students and the instructors. | LOW | HIGH- This home page will be the base for all actions that instructors would like to acces. | Frontend: Talar, Valeria Backend: Tiffanny | Sept. 24
#6 | Student should see their own home page | - Make instructor home page -Home page frontend | 3- The home page requires a fullstack developpement in which the layout and design of the website needs to be implemented while differentiaing between the pages of the students and the instructors. | LOW | HIGH- This home page will be the base for all actions that students would like to acces. | Frontend: Talar, Valeria Backend: Tiffanny | Sept. 24
SPRINT 2
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (0,1,2,3,5,8) | Priority | Risk | Assign
SPRINT 3
Issue # | User Story Title/Task Title | Description/Associated Tasks | Due Date | Priority | Risk | Responsible
SPRINT 4
Issue # | User Story Title/Task Title | Description/Associated Tasks | Due Date | Priority | Risk | Responsible
3