## BURNDOWN CHARTS
SPRINT 1
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (0,1,2,3,5,8) | Priority | Risk | Responsible | Due Date
#1 | User should be able to register an account by creating a username and a password so that the user can access to the Peer Assessment Platform | - Add register page which asks user if user is instructor or student, along with their name, username, and password - Add needed columns to database -Register page css | 5- The user needs to be able to register for an account. Otherwise, the user cannot access the Peer Assessment Platform. Required for initializing a profile and taking advantage of the main fucntion of the app. | HIGH | HIGH- part of main function of the website | Frontend: Talar, Valeria Backend: Mohammed | Sept. 20
#2 | User should get a nice error message when the username is no longer available or when the password format is wrong to finalize their registration | - Make it so when user enters a username no longer available, instead they are brought back to the register page and get a nice error message there. | 4- The user needs to be notified if their username/password meets the requirements to register for an account | MED | HIGH- It is important for users to be notified. Howver, it is not a feature with the most priority. | Joseph | Sept. 20
#3 | User should get a nice error message when the username and password does not match a user when logging in | - Make it so when user enters a username and password not found, they are brought back to the login page with a nice error message there. | 4- The user should be notified about their entry being denied due to the username/password not matching as it is the foundation of one's entry to the webiste | MED | HIGH- It is extremely important for this step to be implemented as it allow users to be granted use of the website | Joseph | Sept. 25
#4 | User should be able to login with their credentials so that they can access the platform | - Add login page which asks user their username and password, communicates with database and gives user session variables - Login page frontend | 4- Same idea as issue#2 and issue#3 | HIGH- Essential for registered users to login onto the Peer Assement platform to be able to access its function. Part of the main part of the website. | HIGH- Messing up this task implies that the website won't work | Frontend: Talar, Valeria Backend: Samuel | Sept. 22
#5 | Instructor should see their own home page | - Make instructor home page -Home page frontend | 3- The home page requires a fullstack developpement in which the layout and design of the website needs to be implemented while differentiaing between the pages of the students and the instructors. | LOW | HIGH- This home page will be the base for all actions that instructors would like to acces. | Frontend: Talar, Valeria Backend: Tiffanny | Sept. 24
#6 | Student should see their own home page | - Make instructor home page -Home page frontend | 3- The home page requires a fullstack developpement in which the layout and design of the website needs to be implemented while differentiaing between the pages of the students and the instructors. | LOW | HIGH- This home page will be the base for all actions that students would like to acces. | Frontend: Talar, Valeria Backend: Tiffanny | Sept. 24
SPRINT 2
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (0,1,2,3,4) | Priority | Risk | Dependencies | Responsible | Reviewer | Due Date
45 | Enhancement: Make groups in database appear on home pages | - Make student home page display groups student is in -Make instructor home page display groups intructor is in - Add group, new users into database - Create new URL dispatchers with functions | 3 | HIGH | HIGH- These home pages will be the base for everything after | None (from this sprint) | Samuel | Talar | Early - October 14
| Design Sitemap | - Design and update site map and project architecture for this sprint (https://miro.com/app/board/uXjVKg3pHwg=/?inviteKey=SkJEQkVPNzU1elhtUTltb253Y3hUT2dVMTZ3ZFUwUGNzSktiYTh3em4wMUxkdDdZb0Fta0VqT25HTU5vbDc4QXwzMDc0NDU3MzYzMTM3NDQ4OTg3fDI= ) | 2 | HIGH | HIGH |  | Samuel |  | Early as possible - October 7
52 | Enhancement: Student should be able to see a list of his team mates | -Extract team number from URL -Get user_id from session -Query students based on team_number -Format student data as list of dictionaries -Send student list to frontend | 2 | HIGH | HIGH - Being done incoectly could lead to issues in the display of the teams on the student dashboard | None (from this sprint) | Tiffany | Samuel | Mid - October 20th
53 | Instructor should be able to create a group of students by manually adding them | - Allow for retrieval and processing of group name and user names from frontend into a group with all infos saved into a database - Internal check if the user is present in the database, with an error appearing if the user doesn't exist - Creating a link between the users with the group with a particular project ID | 3 | HIGH | MEDIUM- Being done incorrectly can lead to issues, but the page is not dependent on further pages | None (from this sprint) | Joseph | Samuel | Late - October 28
54 | Instructor should be able to create a group of students from a CSV upload | - Allow for retrieval and processing of multiple groups outlined in a .csv file into the database - Internal check if a user is present in the database (error message displayed with what user in which group doesn't exist), if the file is a .csv file or too large - Creating a link between the users with their given group with a project ID | 3 | MEDIUM | MEDIUM- Being done incorrectly can lead to issues, but the page is not dependent on further pages | None (from this sprint) | Joseph | Samuel | Late - October 28
| Host website | - Deployed the website on Python Anywhere | 2 | MEDIUM | HIGH - Being done incorrectly would prevent the website from displaying correctly | Everything (to reflect final version) | Tiffany | Everyone | Mid - October 20th
55 | Student should be able to see the students of a selected team from the homepage |  | 3 | HIGH | HIGH - If incorrectly done, the students can not procede to select a student from the team and assess them |  | Valeria
56 | Student should be able to rate a selected student from a team based on 4 critera over 5 points |  | 2 | HIGH | MEDIUM- Being done incorrectly can lead to issues, but further page are not dependent this page |  | Valeria
60 | Instructor should be able to create a group of students from a CSV upload or from a manual form | -Allows instructors to create groups of students either by uploading a CSV file or through a manual entry form. -CSV Upload: Instructors can upload a CSV file containing student information, which the system will process to automatically create groups. -Manual Form: Instructors can fill in group details manually, adding student usernames individually to create a customized group. -Provides flexibility in group creation based on instructor preferences or data availability. | 5 | HIGH | High- Being done incorrectly can lead to a whole set of functions not being implemented in the peer assessment review project as the project relies on the creation of teams | None (from this sprint) | Talar | Valeria & Mohammad | Early- October 20th
68 | Instructor should be able to acces the create group page from their home page | -Allows instructors to create groups of students either by redirecting them from their page to the create group page where it has the forms/csv they need to fill using a button | 3 | MEDIUM | High- Being done iccorectly means the intructor can't acces the form to add a group | None (from this sprint) | Talar | Valeria & Mohammad | Late - October 28th
SPRINT 3
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (0,1,2,3,4) | Priority | Risk | Dependencies | Responsible | Reviewer | Due Date
86 | Add new URLs, views, and HTML files for sprint 3 | To faciliate sprint 3, add URL: student/teamRatings/int:team_id Function: studentTeamRatings URL: student/teamRatingsDownload/int:team_id Function: studentTeamRatingsDownload URL: instructor/teamRatings/int:team_id Function: instructorTeamRatings URL: instructor/teamRatingsDownload/int:team_id Function: instructorTeamRatingsDownload URL: instructor/overallRatings Function: instructorOverallRatings URL: instructor/overallRatingsDownload Function: overallRatingsDownload and several HTML files | 1 | HIGH- This has to be done first if it is going to help for this sprint | MEDIUM- Any typos will have an affect on the rest of the teammembers parts, but they easily fixable | None for this sprint | Samuel | Talar | November 3, 2024 (Early)
90 | Display teammembers and delete them on instructor page | Add button on instructor page to view and delete teammembers Create URL for page to view teammembers Create HTML template to view teammembers Create view to view teammembers | 3 | MEDIUM- Not necessary, but a helpful addition | LOW- This page doesn't lead to any other pages or has any important functionality | None for this sprint | Samuel | Talar | 2024-11-14
88 | Remove open/close buttons | Remove team open/close buttons on instructor page Remove any use of it in the backend (from views, models) Remove mention of a team being open or closed on all templates | 1 | LOW- The button is unused anyway, but it is redundant | LOW - The removal of the button will not affect anything | None for this sprint | Samuel | Joseph | 2024-11-14
98 | Set Up Views for student team ratings | Query team data by team_id; Compile ratings, handling missing values with blanck entries; Render the data as JSON for frontend | 3 | MEDIUM- Does not really affect teammates'work | MEDIUM- Does not really affect teammates'work | None for this sprint | Tiffany | Samuel | 2024-11-14
99 | Export Student team ratings to CSV | Write cSV headers and populate data rows; Set up HTTP response with CSV file download | 3 | MEDIUM- Does not really affect teammates'work | MEDIUM- Does not really affect teammates'work | None for this sprint | Tiffany | Samuel | 2024-11-14
108 | Instructor should be able to see overall ratings | From button "Overall Team Ratings", opens page called Overall Team Ratings. Create table displaying all the students' overall ratings for each aspect, as well as their information. Add button for downloading the table's data into a CSV file. - Set up HTML and corresponding CSS for it. | 2 | MEDIUM - Table has to be displayed, but doesn't affect the upcoming tasks | MEDIUM- Table's data comes from backend | Data about student from backend | Valeria | Joseph | 2024-11-14
111 | Fix consistencies in page presentation | Make sure that the pages have similar layout, buttons and overall aesthetic for better visuals. Modify elements that do not facilitate the user's visual experience. | 2 | MEDIUM- Does not really affect teammates'work | LOW- Does not affect any functionality | None for this sprint | Valeria | Talar | 2024-11-14
102 | Instructor and student should be able to see ratings | Create HTML template for students to view ratings Create HTML template for instructors to view students team ratings Create CSS files to match the respective HTML pages Create table for students and instructor HTML pages to correctly display the ratings Create download csv button in both HTML pages to be able to display the tables as a CSV file | 3 | MEDIUM - Table has to be displayed, and affects the ratings function of the task | MEDIUM- Table's data comes from backend | None for this sprint | Talar
103 | Add basic backend functionality of instructor viewing overall ratings of all his students | Query team data by double loop (upper loop by team id, lower loop by user id) and a third loop with teammate id; Compile ratings, handling missing values with "-" entry; Render the data as JSON for frontend | 3 | HIGH - Essential functionality for the sprint | Low - Doesn't affect the rest of the sprint | None for this sprint | Joseph | Samuel | November 13, 2024 (Late)
106 | Export instructor overall ratings to CSV file | Write CSV headers and populate data rows; Set up HTTP response with CSV file download | 3 | HIGH - Essential functionality for the sprint | Low - Doesn't affect the rest of the sprint | None for this sprint | Joseph | Samuel | November 14, 2024 (Late)
117 | Instructor tean rating downlaoad | Instructors needed an option to download the team’s aggregated ratings as a CSV file for offline access or further analysis. | 3 | HIGH - Essential functionality for the sprint | Medium | None for this sprint | Mohammed | Samuel | November 14, 2024 (Late)
116 | Display detailed team rating | An instructor required a feature to view compiled ratings for each team member across various categories (such as cooperation, conceptual understanding, practical skills, and work ethic). The system also needed to account for team members who had not yet been rated by displaying their values as blank. | 3 | HIGH - Essential functionality for the sprint | Medium | None for this sprint | Mohammed | Samuel | November 14, 2024 (Late)
SPRINT 4
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (0,1,2,3,4) | Priority | Risk | Dependencies | Responsible | Reviewer | Due Date
118 | Add ability to delete group and add user to group | Have the new abilities for an instructor to both: Delete a group - Delete all database entries if so Add new users to existing group | 2 | Medium - Nice to have, not necessary | Medium - it touches the database but doesnt do much to it | None | Samuel | Tiffanny | 2024-11-25
23 | Split project into directory based architecture | - Create apps 'userAuth', 'student', 'instructor' - Move views into correct new app - Move URLs into correct new app - Rename views, links, css, URLs to fit new architecture - Move all templates into new static folder - Test website still functional | 4 | High - This has to be done first to avoid merge conflicts | High - This touches the whole website, and an error is costly | Everything | Samuel | Talar | 2024-11-18
131 | Fix styling issues and ensure a uniform styling structure for all frontend pages | - Analyze styling differences across all frontend pages and modify them - Add a pointer you can make the logout settings button styling on the student page like the instructors - Add a button that allows to get back to instructor/student (add homepage button) - Fix images - Adjust header and footer wherever it looks different | 2 | Low- Since it concerns only styling issues, doing this take doesn't affect any others and the webiste could still properly function without them | Low - None of the changes have a risk of affecting other stories | None | Talar | Samuel | Novembre 28
138 | Add user settings page for student and instructor | (Frontend & Backend) Added user settings page for student and instructor (instructorSettings.html and studentSettings.html) Ability for user to change: username, Password, Email, name Also made sure that the settings route for all the pages is correct and accessible everywhere. | 2 | Medium - Doesn't impact other aspects, but necessary funtionality | Medium - it touches the database but doesnt do much to it | None | Valeria, Mohammed | Joseph | 2024-11-25
141-150 | Write acceptance tests | Write acceptance tests for all sprints except sprint 3 | 3 | Low- Useful, but not necessary | Low - It doesn't touch anything | None | Mohammed | Talar | 2024-11-28
123 | Create test cases in tests.py for instructor and student apps | -Created 15 test cases in tests.py | 3 | Low - Useful but not necessary | High - An error would not let the app run | Everything | Joseph | Samuel | 2024-11-26