## BURNDOWN CHARTS
SPRINT 1
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (0,1,2,3,5,8) | Priority | Risk | Responsible | Due Date
#1 | User should be able to register an account by creating a username and a password so that the user can access to the Peer Assessment Platform | - Add register page which asks user if user is instructor or student, along with their name, username, and password - Add needed columns to database -Register page css | 5- The user needs to be able to register for an account. Otherwise, the user cannot access the Peer Assessment Platform. Required for initializing a profile and taking advantage of the main fucntion of the app. | HIGH | HIGH- part of main function of the website | Frontend: Talar, Valeria Backend: Mohammed | Sept. 20
#2 | User should get a nice error message when the username is no longer available or when the password format is wrong to finalize their registration | - Make it so when user enters a username no longer available, instead they are brought back to the register page and get a nice error message there. | 4- The user needs to be notified if their username/password meets the requirements to register for an account | MED | HIGH- It is important for users to be notified. Howver, it is not a feature with the most priority. | Joseph | Sept. 20
#3 | User should get a nice error message when the username and password does not match a user when logging in | - Make it so when user enters a username and password not found, they are brought back to the login page with a nice error message there. | 4- The user should be notified about their entry being denied due to the username/password not matching as it is the foundation of one's entry to the webiste | MED | HIGH- It is extremely important for this step to be implemented as it allow users to be granted use of the website | Joseph | Sept. 25
#4 | User should be able to login with their credentials so that they can access the platform | - Add login page which asks user their username and password, communicates with database and gives user session variables - Login page frontend | 4- Same idea as issue#2 and issue#3 | HIGH- Essential for registered users to login onto the Peer Assement platform to be able to access its function. Part of the main part of the website. | HIGH- Messing up this task implies that the website won't work | Frontend: Talar, Valeria Backend: Samuel | Sept. 22
#5 | Instructor should see their own home page | - Make instructor home page -Home page frontend | 3- The home page requires a fullstack developpement in which the layout and design of the website needs to be implemented while differentiaing between the pages of the students and the instructors. | LOW | HIGH- This home page will be the base for all actions that instructors would like to acces. | Frontend: Talar, Valeria Backend: Tiffanny | Sept. 24
#6 | Student should see their own home page | - Make instructor home page -Home page frontend | 3- The home page requires a fullstack developpement in which the layout and design of the website needs to be implemented while differentiaing between the pages of the students and the instructors. | LOW | HIGH- This home page will be the base for all actions that students would like to acces. | Frontend: Talar, Valeria Backend: Tiffanny | Sept. 24
SPRINT 2
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (0,1,2,3,4) | Priority | Risk | Dependencies | Responsible | Reviewer | Due Date
45 | Enhancement: Make groups in database appear on home pages | - Make student home page display groups student is in -Make instructor home page display groups intructor is in - Add group, new users into database - Create new URL dispatchers with functions | 3 | HIGH | HIGH- These home pages will be the base for everything after | None (from this sprint) | Samuel | Talar | Early - October 14
| Design Sitemap | - Design and update site map and project architecture for this sprint (https://miro.com/app/board/uXjVKg3pHwg=/?inviteKey=SkJEQkVPNzU1elhtUTltb253Y3hUT2dVMTZ3ZFUwUGNzSktiYTh3em4wMUxkdDdZb0Fta0VqT25HTU5vbDc4QXwzMDc0NDU3MzYzMTM3NDQ4OTg3fDI= ) | 2 | HIGH | HIGH |  | Samuel |  | Early as possible - October 7
52 | Enhancement: Student should be able to see a list of his team mates | -Extract team number from URL -Get user_id from session -Query students based on team_number -Format student data as list of dictionaries -Send student list to frontend | 2 | HIGH | HIGH - Being done incoectly could lead to issues in the display of the teams on the student dashboard | None (from this sprint) | Tiffany | Samuel | Mid - October 20th
53 | Instructor should be able to create a group of students by manually adding them | - Allow for retrieval and processing of group name and user names from frontend into a group with all infos saved into a database - Internal check if the user is present in the database, with an error appearing if the user doesn't exist - Creating a link between the users with the group with a particular project ID | 3 | HIGH | MEDIUM- Being done incorrectly can lead to issues, but the page is not dependent on further pages | None (from this sprint) | Joseph | Samuel | Late - October 28
54 | Instructor should be able to create a group of students from a CSV upload | - Allow for retrieval and processing of multiple groups outlined in a .csv file into the database - Internal check if a user is present in the database (error message displayed with what user in which group doesn't exist), if the file is a .csv file or too large - Creating a link between the users with their given group with a project ID | 3 | MEDIUM | MEDIUM- Being done incorrectly can lead to issues, but the page is not dependent on further pages | None (from this sprint) | Joseph | Samuel | Late - October 28
| Host website | - Deployed the website on Python Anywhere | 2 | MEDIUM | HIGH - Being done incorrectly would prevent the website from displaying correctly | Everything (to reflect final version) | Tiffany | Everyone | Mid - October 20th
55 | Student should be able to see the students of a selected team from the homepage |  | 3 | HIGH | HIGH - If incorrectly done, the students can not procede to select a student from the team and assess them |  | Valeria
56 | Student should be able to rate a selected student from a team based on 4 critera over 5 points |  | 2 | HIGH | MEDIUM- Being done incorrectly can lead to issues, but further page are not dependent this page |  | Valeria
60 | Instructor should be able to create a group of students from a CSV upload or from a manual form | -Allows instructors to create groups of students either by uploading a CSV file or through a manual entry form. -CSV Upload: Instructors can upload a CSV file containing student information, which the system will process to automatically create groups. -Manual Form: Instructors can fill in group details manually, adding student usernames individually to create a customized group. -Provides flexibility in group creation based on instructor preferences or data availability. | 5 | HIGH | High- Being done incorrectly can lead to a whole set of functions not being implemented in the peer assessment review project as the project relies on the creation of teams | None (from this sprint) | Talar | Valeria & Mohammad | Early- October 20th
68 | Instructor should be able to acces the create group page from their home page | -Allows instructors to create groups of students either by redirecting them from their page to the create group page where it has the forms/csv they need to fill using a button | 3 | MEDIUM | High- Being done iccorectly means the intructor can't acces the form to add a group | None (from this sprint) | Talar | Valeria & Mohammad | Early- October 28th
SPRINT 3
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (0,1,2,3,4) | Priority | Risk | Depencies | Responsible | Reviewer | Due Date